## Tasks and Timeline
DEC KKU US
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE - July | [19 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Setting/Prerequisite |  | 2024-03-20 | 2024-03-29
Priject Mygration from CT Scan |  | 2024-03-20 | 2024-03-20 | 1 | Masum | Pending | bar: WEEK 1 M to WEEK 1 F
Database Finalize |  | 2024-03-20 | 2024-03-21 | 2 | Masum | Pending | bar: WEEK 1 M to WEEK 1 F
User registration |  | 2024-03-21 | 2024-03-21 | 1 | Sakib | Pending | bar: WEEK 1 M to WEEK 1 F
Organization Setup |  | 2024-03-22 | 2024-03-22 | 1 | Sakib | Pending | bar: WEEK 2 M
Exam information |  | 2024-03-25 | 2024-03-25 | 1 | Sakib | Pending | bar: WEEK 2 T to WEEK 2 R
Initial Progress Meeting |  | 2024-03-25 | 2024-03-25 | 1 | Masum | Pending
Worklist |  | 2024-03-20 | 2024-03-29
Study Worklist |  | 2024-03-21 | 2024-03-28 | 6 | Sakib | Pending | bar: WEEK 1 W to WEEK 1 F
Router Service |  | 2024-03-20 | 2024-03-29
Patient Entry from Client API |  | 2024-03-21 | 2024-03-22 | 2 | Sakib | Pending | bar: WEEK 1 T
Create Study by Import DICOM |  | 2024-03-25 | 2024-03-26 | 2 | Sakib | Pending
Extract Image from DICOM and store in separate folder |  | 2024-03-22 | 2024-03-25 | 2 | Masum
Progress Meeting |  | 2024-03-29 | 2024-03-29 | 1 | Masum | Pending

## Sheet1
Developer
Shanto
Fahim
Akash
Arif
Sakib
Omor